## Stakeholder Register
RetailCo — Stakeholder Register
This is an independent portfolio case study. No real stakeholder interviews were conducted. Stakeholder roles, interests, influence levels, needs and engagement approaches are simulated for BA practice. • Stakeholder classifications are simulated assumptions. • No real stakeholder meetings occurred. • Stakeholder information is not presented as real organizational evidence. • Supplier/lead-time involvement is a hypothesis consideration, not proof of a root cause. • Proposed workshops, validation and UAT activities are simulated BA activities.
Stakeholder | Role | Interest | Influence | Information Needed | BA Engagement
Business Sponsor | Simulated executive sponsor responsible for business objectives and overall direction | High | High | Executive KPIs, business priorities, solution options, business-case considerations | Validate scope, objectives, key requirements and final recommendation
Sales Manager | Simulated owner of sales performance and commercial reporting | High | High | Revenue, units sold and margin by category, brand, city, store format and channel | Validate business questions, KPI requirements and reporting needs
Inventory Manager | Simulated owner of inventory monitoring and replenishment | High | High | Inventory exceptions, including transactions below reorder level, and replenishment-related information | Validate inventory requirements, business rules, process needs and UAT scenarios
Finance Manager | Simulated owner of financial reporting and profitability analysis | High | Medium-High | Revenue, cost and margin definitions and calculations | Validate KPI definitions, formulas and financial business rules
Operations Manager | Simulated owner of operational performance across stores and channels | Medium | Medium-High | Store/channel performance and operational exception information | Contribute to process modelling, operational requirements and simulated pain-point analysis
Procurement Manager | Simulated procurement and supplier-management role | Medium | Medium | Supplier and lead-time information where relevant to inventory hypotheses | Consult when evaluating supplier or lead-time-related hypotheses; do not assume lead time is a root cause
Store Manager | Simulated day-to-day operational and reporting user | High | Low-Medium | Actionable sales and inventory exceptions relevant to store operations | Provide simulated end-user needs and usability considerations for reporting/UAT
BI / Data Analyst | Simulated technical and data-analysis role | High | Low-Medium | Data definitions, data quality findings, KPI formulas and reporting logic | Support data validation, KPI definitions, analysis and reporting requirements
IT Representative | Simulated technical stakeholder responsible for system considerations | Medium | Medium-High | Security, access, technical constraints, feasibility and non-functional requirements | Review non-functional requirements and solution feasibility considerations

## Power-Interest Matrix
RetailCo — Power-Interest Matrix (Simulated Stakeholders)
Positions are illustrative, based on each simulated role's typical scope of authority and stake in this project. Procurement Manager is kept at Medium Power / Medium Interest rather than forced into a High/Low quadrant.
| LOW INTEREST | MEDIUM INTEREST | HIGH INTEREST
HIGH POWER | KEEP SATISFIED Operations Manager IT Representative |  | MANAGE CLOSELY Business Sponsor Sales Manager Inventory Manager Finance Manager
MEDIUM POWER |  | CONSULT Procurement Manager (supplier/lead-time hypotheses only)
LOW POWER | MONITOR (No stakeholders currently mapped to this quadrant) |  | KEEP INFORMED Store Manager BI / Data Analyst
Engagement strategy by quadrant:
• Manage Closely (High Power / High Interest) — involve in scope, requirements, KPI decisions and recommendation validation.
• Keep Satisfied (High Power / Low Interest) — provide relevant updates and involve when operational or technical decisions require input.
• Consult (Medium Power / Medium Interest) — consult when supplier or lead-time information is relevant; do not assume it is a confirmed root cause.
• Keep Informed (Low Power / High Interest) — keep informed and involved in requirements, usability, data definitions and validation activities.
• Monitor (Low Power / Low Interest) — no stakeholders currently identified.